

**Item 11 (3)**

**Exception Report: Transforming Learning Disabilities**

|  |  |
| --- | --- |
| Summary of Project | The Transforming Learning Disabilities programme seeks to transform and integrate the planning, commissioning and delivery of LD services to improve outcomes for those using services and their carers. It is a core strategic priority for the RPB and reflects its statutory duty to promote the integration of LD services. The programme will develop a regional approach informed by local LD strategies in each local authority area |
| Period covered by the report | October 2017 to January 2018 |
| Summary of overall status | Progress on scoping the programme has been slower than anticipated although, following an engagement event in October 2017 and subsequent programme planning sessions a revised programme with clear priorities has been agreed |
| Key Risks | Failure to progress agreed priorities and supporting workstreams due to lack of capacity among participating organisations  Failure to consolidate local strategies into a cohesive regional approach  Lack of direct sponsorship from the RPB |
| Key Issues | Need to ensure that agreed workstreams (1) reflect national requirements emerging from national commissioning guidance, the Ministerial review of LD services and the establishment of pooled funding arrangements for residential care and (2) build on evidenced good practice at local level |
| Key Milestones | Market Position Statement for LD Services – March 2018  Work plans , membership and leads agreed for work streams – 1 March 2018  Mapping current Learning Disability model of service delivery – by end April 2018. |
| Milestones achieved/Outputs (deliverables) completed in last period | Engagement day with providers 19/10/17 outcomes of which have informed agreed priorities and workstreams and the regional Market Position Statement  Outline programme plan and workstream plans agreed and workstream leads identified |
| Shortfalls/Non-completions in last period | None |
| Forecast for next period | Complete programme and workstream plans  Complete regional Market Position Statement for LD Services |
| Financial status | Total ICF allocation for 2017/18 is £30k |