## Summary
Integrated Care Fund 2017-18
Quarter 4 Return Summary
REVENUE
Scheme | Allocation | Total Spend YTD Q4 | Anticipated Full Year Spend
Older people with complex needs and long term conditions, including Dementia and their Carers | 5542956.4 | 5662826.1606 | 5662826.1606
Children with Learning Disabilities and Complex Need and their Carers | 442222 | 325373.45 | 325373.45
Integrated Autism Service | 318200 | 315775.4 | 315775.4
Wales Community Care Information System | 184000 | 183802.5 | 183802.5
Solva Care | 33540 | 33540 | 33540
TOTAL | 6520918.4 | 6521317.5106 | 6521317.5106 | -399.1106
CAPITAL
Scheme | Allocation | Total Spend YTD Q4 | Anticipated Full Year Spend
TOTAL | 1300177 | 1299824.79 | 1299824.79 | 352.21

## Frail and Older People
Regional Allocation | Total regional spend | Regional under/overspend | ICF 2017-18 monitoring |  |  |  | 2018-06-01
5760496.4 | 5880168.6606 | -119672.2606 | West Wales - Frail and Older People
Region |  | Category |  | Performance
West Wales |  | Frail and Older people |  | Projected outcomes and outputs | Outcomes to date | Expenditure
Ref | Funding Allocation | Service / activity description | Specific area or whole region? | Include a benchmark or target for reference against | Q4 | Spend to Date | Over or underspend | Further information
| 74000 | Regional Coordination (Carmarthenshire CC and Hywel Dda UHB) (Whole region) | Whole Region | Co-ordination of Regional ICF Programme | Ongoing co-ordination of 17/18 programme. | 73242.1 | 757.9
| 94910 | Pooled funds and service integration | Whole Region | Development of a regional approach to pooled funds | collation of pooled fund performance and financial data -production of pooled fund agreement -regional options appraisal for community equipment stores -set up and facilitation of Service Integration and Pooled Funds Programme Board and associated working groups -programme facilitation (salary) | 94975.66 | -65.66 | A clear plan for delivery of the appraisal by 31/3/18 was developed. Timescales have slipped due to the availability of key personnel
| 66841 | IAA/ prevention including regional supporting social enterprises | Whole Region | Development of a regional approach to IAA, prevention and social enterprise development | Development of IAA /Preventions boards to steer regional process. | 65645.03 | 1195.97 | Draft regional preventions framework in the process of being finalised.
| 66841 | Integrated commissioning | Whole Region | Development of a regional approach to integrated commissioning | Development of IC board to steer regional process. | 68914.85 | -2073.85
| 30000 | LD Transformation | Whole Region | Implementing a regional approach to LD and Transformation | Development of LDP group to steer regional process. | 29934.34 | 65.66
| 184000 | WCCIS Implementation | Whole Region | Implementing WCCIS across the region | Development of WCCIS board to steer regional process. | 183802.5 | 197.5
| 20000 | Supporting Social Enterprises | Whole Region | Social Enterprise development |  | 19650 | 350 | Actions reallocated to IAA/Prevention priority. Underspend will be addressed by the end of Q4.
| 33540 | Solva Care | Whole Region |  |  | 33540 | 0 | Project fully spent and invoiced. WG process to re-claim underway.
| 1877 | Now is the Time: Pembrokeshire Time Banking | Pembrokeshire | No. of timebanks established | 1 timebank up and running, with 2 starting in early April | 1877 | 0 | Newport Timebank is now up and running, participants are earning credits and the first vouchers have been issued. The VC Gallery have trained their Brokers and the Haverfordwest Timebank will start running after Easter. 6 individuals are having training to run a Timebank on the Mount Estate in Milford Haven after Easter
|  |  |  | No. of people actively engaging in timebanking | 26 people actively engaging in timebanking
|  |  |  | No. of hours earned and exchanged | 74 credits earned 6 spent |  |  | No hours earned as yet, however once the current ‘trainees’ begin publicising the timebank, then hours will begin being earned.
| 160712 | PIVOT – Pembrokeshire Intermediate Voluntary Organisations Team | Pembrokeshire | No. of hospital admissions prevented | 349 hospital admissions prevented | 160000 | 712
|  |  |  | No. of supported discharges | 261 supported discharges
|  |  |  | Bed days saved | 3855 Bed days saved
| 30000 | Community Connectors (Active & Connected Communities) | Pembrokeshire | No. of people receiving I,A&A to help manage their own health and wellbeing | 555 | 30000 | 0
|  |  |  | No. of volunteer led activities established | 2
|  |  |  | % reporting improved QoL | 100% of those responding report improved QoL
| 34000 | Third sector Health and Well-being Facilitator | Pembrokeshire | No. new services developed to meet gaps | 5 | 34000 | 0
|  |  |  | No. of Pembs services registered on infoengine (new registrations) | 153 new organisations registered. 210 new services registered.
| 30000 | Caring Communities Innovations Grants | Pembrokeshire | No. of grants distributed | 5 | 30000 | 0
|  |  |  | Value of grants distributed | 30000
| 75000 | Commissioning - Brokerage and Quality Assurance | Pembrokeshire |  |  | 77895.45 | -2895.45
H2 | 50000 | Older peoples Service | Pembrokeshire | Number of additional community frailty clinics developed | 0 | 50000.24 | -0.24 | There are currently 5 clinics offering Comprehensive Geriatric Assessments within the Older Adults Assessment and Liaison Service. Several surgeries have been approached within the GP Clusters and the response has been positive. Clinics will be developed in response to clinical demand i.e. clinics will be held where the number of referrals indicate the need so that the service will be responsive. To note – clinics have had to be cancelled on occasions due to Consultant work demand and availability of physiotherapists.
|  |  |  | No of patients seen in MDT led Community Frailty Clinics | 180
|  |  |  | No of MDT / CRT meetings attended across North and South Pembrokeshire | 36 |  |  | The CRTs are continuing to be piloted in two surgeries through the North and South of Pembrokeshire supported by the Older Adults CNSs. The CRTs have resulted in several direct referrals to the Service which has enabled the patient in some cases to be seen by the MDT in frailty clinics the next day. This has resulted in admission avoidance. The MDT review is underway.
|  |  |  | Number of new patients (referred via CRT) | 20
|  |  |  | No of Rapid Access Clinics developed | 0 |  |  | This is unchanged from last quarter. Medical teams are looking at various ways of working e.g. front door CGA’s and rapid turnaround that may not entail clinics.
|  |  |  | Number of domiciliary visits provided to patients by frailty CNSs across North and South Pembrokeshire | 329
|  |  |  | Number of patient and user experience questionnaires collected in the quarter | 0 |  |  | Patient questionnaire due to be piloted by the end of April. Positive feedback has been given verbally from service users.
|  |  |  | Development of a Falls Service |  |  |  | Of note there has been a new balance class commenced in the North. Frailty pathway is being developed for use in the community.
| 24800 | Developing Integrated Community Teams – Programme Manager | Pembrokeshire |  |  | 17473.39 | 7326.61
H4 | 200000 | Community Resource Team / Care at Home | Pembrokeshire | Business case to be developed to increase workforce capacity to match demand of care at home service | Funding was received for additional 10 WTE band 3s in October 2017 | 199876.3308 | 123.6692 | The Care at Home Team provide End of Life Care to patients aged 18 years and over across the North and South Localities of Pembrokeshire. The Care at Home Registered Nurse Co-ordinator has direct line management of the team, including recruitment, training and development. The Team currently comprises of 17.6 WTE experienced Senior Health Care Workers. A further 1WTE will commence in April and 1.8 WTE is currently out to advert. Bank is currently being utilised to ensure maximum capacity until full establishment are recruited into. Care is provided between the hours of 08.00hrs-22.00hrs with two shift patterns from 08.00hrs-20.00hrs and 10.00hrs-22.00hrs.
|  |  |  | Total number of referrals per quarter | 125
|  |  |  | Number of patients who received end of life care in per quarter. | 59
|  |  |  | Number of patients who received care at home in relation to admission avoidance /discharge from hospital | 45
|  |  |  | Number of patients with complex care needs seen at home. | 11
| 247563 | Reablement | Pembrokeshire | The number of people who have completed a period of reablement | 306 | 258023.77 | -10460.77
|  |  |  | The number of people in reablement on the last day of the period. | 148
|  |  |  | The average no. of weeks for a reablement intervention. | 5
|  |  |  | The % of people who leave reablement with no long term domiciliary care needs. | 72%
|  |  |  | The % of people who leave reablement with reduced long term domiciliary care needs. | 8.5%
|  |  |  | 20a - % of adults who completed a period of reablement; and have a reduced package of care and support 6 months later | 22%
|  |  |  | 20b - % of adults who completed a period of reablement; and have no package of care and support 6 months later | 61%
P5 | 40000 | Releasing Time to Care (OT) | Pembrokeshire | Citizens get the right care and support, as early as possible. Percentage of people whose care and support has helped them have a better quality of life. Number of care hours saved | 65 clients assessed. 24 packages reduced safely, 12 packages in the rocess of safe reduction. 220.75 care hours per week were saved, and a further 120 hours per week were avoided. At February 2018, the project had made a financial saving of £134,645 (full year effect of all reductions made in 2017/18). A further £39,638 was avoided. | 40554 | -554 | Project has been nominated for 2 Social Care Accolades. Video case studies have been filmed with individuals who worked with the project. Videos are to be translated but see link to sample case study video: https://cdn.pembrokeshire.gov.uk/videos/social-care-vid.html End of year infographic Quarter 4 case study:
H6/H7 | 273130 | Multi Agency Support Team Nurse, Occupational & Physiotherapy (MAST) | Pembrokeshire | Total no of patients assessed in A&E/ACDU by MAST | 681 | 272985.0698 | 144.9302 | Video case studies have been filmed with individuals who worked with the project.
|  |  |  | No assessed by MAST in A&E/ACDU at weekends/Bank Holidays | 215
|  |  |  | No assessed not admitted to an acute bed | 64%
|  |  |  | No of bed days saved Cost of beds saved | 1660 (10 days per person not admitted to an acute bed) £498,000
|  |  |  | No of patients S/B MAST referred to community teams | 196
|  |  |  | No of urgent community referrals responded to within 2 days | 234
|  |  |  | % of people surveyed who report they are able to do the things that matter to them | 93%
H3 | 100000 | Acute Response Team Enhancement | Pembrokeshire | Reduce unnecessary A&E presentations and hospital admissions / re-admissions. | 1949 | 99714.51 | 285.49 | In Q4 the service responded to 456 patient referrals which compares with 513, 511, 469 for preceding quarters. This represents a prevailing demand for the service and also capacity for the service to respond to that demand.
|  |  |  | Improve ART's acute hospital ward 'in-reach' and integrated working with the Joint Discharge Team to better identify patients eligible and appropriate for the ART service. |  |  |  | ART service and 'Coordinator' role continue to work interactively with Joint Discharge Team, daily Bed Meeting and weekly Community Pull Meeting in proactively identifying patients suitable for early discharge with ART support.
|  |  |  | Improve ART's acute hospital 'in-reach' and support to ward areas to facilitate early and safe discharge. | 473 |  |  | Development of the ‘Coordinator’ role within the service continues to effectively support ART’s effective in-reach to acute ward areas / A&E and liaison with community teams in facilitating and expediting discharge. Acute in-reach in Q4 facilitated 144 (32%) of total referrals which compares with 155, 174, 172 and 70 in preceding quarters. A&E in-reach in Q4 facilitated 13 (2.9%) of total referrals which compares with 28, 21, 20 and 9 in preceding quarters
|  |  |  | Accept more referrals from A&E; | 62
|  |  |  | Maintain ART’s capacity to readily accept referrals for patients requiring social care / awaiting Reablement upon discharge. | 61 |  |  | enabled ART to continue ‘bridging the gap’ in responding to referrals for patients requiring social care / awaiting Reablement on discharge that otherwise would have resulted in delayed discharges. Q4 saw 12 patients supported representing approximately 47 acute bed days saved. Whilst there has been a rise in the number of patients referred in Q4, the duration on ART’s caseload has reduced resulting in an overall reduction in bed days saved compared to previous quarters
|  |  |  | Consolidate availability of care for Miami J Collar patients (typically resulting in a 12 week hospital stay) | 20 |  |  | Additional staff resource has enabled ART to continue accepting referrals for patients requiring Miami Collar care following #cervical vertebrae / # odontoid peg that otherwise would have resulted in prolonged periods of hospitalisation. Q4 saw 7 patients supported, representing approximately 155 acute bed days saved.
|  |  |  | Collaborating with relevant partners and taking a leading role in developing home based intravenous diuretic therapy for heart failure patients, typically resulting in a 13 day admission on average); |  |  |  | Business case in development with discussions ongoing with British Heart Foundation concerning pathway / protocol development and training / up-skilling of staff.
|  |  |  | Scoping possibilities of developing ART’s capability to deliver to other new patient groups. |  |  |  | Additional staff resource has enabled ART to continue providing an additional rapid response car / clinical nursing crew for the twilight period (17.00-01.00hrs) as part of an ongoing pilot to improve the referral acceptance rate and time of service response to patients referred from the GP Out of Hours Service early evening / overnight. In the pre-pilot period, there was a 90% acceptance rate and the majority of referrals were attended to between 90-120 minutes. Q4 builds upon the consistent improvement in Q2 and Q3, with a 97% acceptance rate and with 77% of referrals attended to within 90 minutes and 64% within 60 minutes.
|  |  |  | Opportunities for further specialised training and up-skilling of staff up to Advance Practice level to optimise clinical effectiveness and improve patient outcomes. |  |  |  | Additional staff resource has enabled the service to maintain its rapid response to patient referrals as well as provide opportunity for staff release for training. This has enabled a senior member of the team to commence an MSc in Advanced Clinical Practice which will support development of the Advanced Nurse Practitioner role in ART. The intention is to support additional staff in order to further up-skill the team and extend the service’s capacity, reach and scope. Additionally, training is currently underway in support of midline vein insertion / administration of intravenous medication will further extend ART’s scope and reach to administer treatments conventionally only available in acute hospital settings.
|  |  |  | Develop improved processes to demonstrate the outcomes and impact of the service as evidence for future service direction and to support sharing of best practice. |  |  |  | ART's data collection system / processes have been reviewed and are substantially improving the quality of monthly reporting pertaining to patient activity / outcomes. The service is currently in the process of developing poster presentations / award submissions as a means of sharing service and patient care improvements / best practice.
% of people whose care and support has helped them have a better quality of life.
% of people who rate the people that provided their help, care and support as excellent or good.
% of people who feel they have been treated with respect.
H1 | 40000 | Intermediate Care Fund Interim Beds - Nursing Care Home | Pembrokeshire |  |  | 40000 | 0 | Funding allocation for April – June. Spend continues with no additional resource allocated.
| 170000 | Intermediate Care Beds [Step Up / Step Down Beds] | Pembrokeshire |  |  | 187852.15 | -17852.15 | No further Information provided by Pembrokeshire
|  | RTTC Sunderland (Slippage |  |  |  | 10000 | -10000 | No further Information provided by Pembrokeshire
| 10000 | Disability Service Review | Carmarthenshire | To commission & complete a report on service provision and care pathways for children, young people and adults with disabilities. |  | 8980.6 | 1019.4 | Report attached providing the outcomes and evidence of completion.
| 54000 | Programme Co-ordination | Carmarthenshire | Agreed programme delivered. Carms IPB advised of progress. Quarterly reporting via RPB to WG within set timescales | Programme co-ordinated and delivered. | 46424.85 | 7575.15 | Challenge sessions took place during February & March which involved each project/scheme lead presenting to the County Integrated Board on outcomes delivered to date, plans for future development & sustainability & funding required. This allowed a mature debate in terms of how schemes should move forward into the net financial year. A link is attached to view all presentations delivered at this session. Two workstreams have now been convened to consider how we can streamline existing ICF investment & ensure schemes are delivering impact for the population.
| 178193 | Community Resilience & Prevention | Carmarthenshire | Engaged with people at tier 1 level. |  | 205945.97 | -27752.97
Delivered prevention awareness sessions to members of the community with improved asset mapping.
|  |  |  | Recruited and trained Dementia Friends. | Recruited 216 dementia friends. Increased assets registered on Dewis to 503.
|  |  |  | Supported Community groups. | 34 community groups supported 190 individuals supported through CUSP
% of those supported reported improved wellbeing outcomes.
|  |  |  | % of those supported by tier 2 service did not require referral to social care. Number of clients supported to discharge from hospital | Average of 84% individuals did not require statutory intervention. 457 calls made
|  |  |  | Number of clients supported to discharge from hospital | 231 individuals supported through the weekend HFH service.
|  | Home from Hospital Enhanced 7 day service |  | Number of clients supported = 98 of which 78 were new |  |  |  | Over the 3 month period 4 clients received 7am calls, 0 received a call between 5-6pm
|  |  |  | C/F from Dec 2017 = 20 |  |  |  | Due to covering weekends the weekend funding also creates capacity to cover more clients in the week
|  |  |  | New clients |  |  |  | Working on a Mon – Fri service we have 1 x 22.5 hour posts vacant.(1x casual post has just been recruited 19/2/18)
|  |  |  | Jan 28 clients |  |  |  | Working on a 7 day service we have 3 x 16 hour post and 1 35 hour post vacant.
|  |  |  | Feb – 29 |  |  |  | By doing a 7 day service this year it has increased our capacity and have been able to support an extra 18 new clients over the same 3 month period.
|  |  |  | Mar – 21 |  |  |  | Figures for this quarter are down a little on the last quarter this is due to not being able to recruit staff and the agency were finding it difficult to cover shifts in January and part of February.
Weekend support
Jan– 3 AM – 0 CA – 3LL = 6 clients had weekend support
18 weekend visits were made
Feb – 4 AM – 2 CA – 2LL = 8 clients had weekend support
31 weekend visits were made
Mar –3 AM – 8 CA – 3LL = 14 Clients had weekend support
47 weekend visits were made.
Total clients that had weekend calls: 28
| 81967 | Therapeutic Intervention Support Workers for Community Hospitals | Carmarthenshire | Number of people discharged home | This information is for both community hospitals. Number of discharges 296. The average length of stay has reduced from 31 days (Q1) to 27.9 days (Q4). | 71978.35 | 9988.65
| 499175 | Community Proactive Care Team | Carmarthenshire | Short Term Assessment Pathway: % of people who have received reablement complete the programme with no requirement for long term care or reduced long term care Commissioned Care Hours. % of referrals received into CRT being deal with by S/T Assessment Pathway Acute Stroke In-reach Intervention: Stroke patients discharged from acute to community. Average Physiotherapy follow up post discharge. % of patients assessed in community within 72 hours of discharge. Compliance with HDUHB target of Physio intervention within 2 weeks of stroke patient discharge | 41.6% 22.5% Data unavailable for Q4 51 3.3 Days 85.3% 100% | 417845.86 | 81329.14 | All patients demonstrate improvements in functional outcome on at least 1 of the 4 outcome measures (see above), with reduced demand for ongoing community services - 46 stroke patients were discharged from the stroke physiotherapy outreach service during January and March 2018 87% of patients were discharged straight from the stroke physiotherapy outreach team (44 out of 51) 13% of patients required ongoing rehabilitation after stroke physiotherapy outreach (7 out of 51); including Community Physiotherapy; NERS. Therefore a large reduction in the demand of stroke patients on the generalist community team.
| 488165 | Rapid Response Domiciliary Care Service | Carmarthenshire | No of people receiving an intervention from the RR service No of escalations of care, including hospitals admissions avoided No of people supported early hospital discharges No of responses from the Telecare alarms | 265 309 64 230 | 431557.2 | 56607.8
| 30000 | Cartref Cynnes Assessment Flats | Carmarthenshire |  | None | 20242.56 | 9757.44 | Due to an inability to place any Older Adults into the two assessment flats within the Extra Care Scheme, the Integrated Services Board decided in February to de-commission ICF investment from this scheme. The self-contained nature of the apartments mean that they are not suitable as a step-down from hospital facility for Older Adults as they are often complex & unstable upon transfer of care. They recover a minimum 24 hours onsite support and this was not available. Costs incurred relate to rental for the apartments.
| 10000 | Health & Social Care Support Worker | Carmarthenshire |  |  | 4608.5 | 5391.5 | Progress in terms of the roll out pf the Non Complex Wound Care interventions has been slow across the Local Authority Care Homes. This is due to staffing issues within the Community Nursing Service and an inability to provide the competency assessment and training to allow the transfer of skills between nursing and senior domiciliary care workers. Work has progressed on scoping a Regional approach with the support of the WW Care Partnership Workforce Programme manager to develop a pilot around a career progression pathway for an integrated H&SC Worker supported by the Bevan Commission. .
| 23309 | Health Activity Co-ordinator | Carmarthenshire | Providing new accessible community venues for Falls Prevention Strength and Balance Exercises (PSI) Increase in the number of falls referrals. Reduce Falls in two residential care homes in Carmarthenshire. | Delivering sessions in 5 venues with numbers of participants increasing during Q4 24 Falls referrals for Q4 April 16/17 a total number of Falls Referrals - 50 April 17/18 a total number of Falls Referrals - 104 increase of 54 referrals within a year an increase of 108% 7 x Care workers and 1x Physio Tech are currently undergoing CBE/OEP Integrated training through Later Life Training with contact days from Health & Activity Coordinator in preparation for Second Pilot planned for September 2018. | 24974.97 | -1665.97 | Health & Activity Coordinator Specialist Populations has led the two sessions with the Care Workers from each setting assisting to improve their confidence and skills to deliver the sessions long term. The Care Workers now feel confident to lead part of the sessions being delivered and by the end of April will be confident to take over the sessions with ongoing support from Health & Activity Coordinator. Llys y Bryn had a 3 week closure to the public during the pilot so the sessions with Health & Activity Coordinator have been extended to end of April/May for handover. March 2018 starts training for second pilot at Cartref Cynin’s and Awel Twit. 7 x Care workers and 1x Physio Tech are currently undergoing CBE/OEP Integrated training through Later Life Training with contact days from Health & Activity Coordinator in preparation for Second Pilot planned for September 2018.
| 155502 | Central Review Team | Carmarthenshire | Number of reviews completed | 639 | 160747.09 | -5245.09 | The complex review Team consisting of 5 members of staff equivalent to 4.5 WTE are now all in post. The figures reported for the year are taking into the account that the team have only been a full complement since September 2017. The team have ensured that people are receiving the appropriate amount of care to meet their needs and this has released capacity within care provision in the community. This has supported timely discharges from hospital reducing delayed transfer of care. Those people waiting a review have reduced by 30%. With the implementation of the Social Services and Well-being Act and the statutory duty to assess utilising 5 elements of assessment, everyone overdue a review requires a new assessment which takes more time but is comprehensive. This has been beneficial as it has encouraged co-production, concentrating on strengths and capabilities which is having a positive outcome for most people receiving care. Moving forward we anticipate continued success in reducing the number of people waiting for a review with a positive affect for both the person and the department with regard to commissioning of services.
| 73446 | Frailty Support Workers (Acute Wards) | Carmarthenshire |  | April 16/17 a total number of Falls Referrals - 50 total number of Falls Referrals - 104 | 100319.49 | -26873.49 | Project completed
increase of 54 referrals within a year an increase of 108%
| 86661 | Reablement Occupational Therapist’s | Carmarthenshire | % of people who have received reablement who complete with no requirement for long term care % who have reduced long term care Reduction in commissioned care hours Number of people who received reablement in the quarter | 42.3% 44.8% 9441.75 hours 320 | 79467.72 | 7193.28
-1794.6
| 704732 | TOCALS | Carmarthenshire | GGH front of house TOCALS Number Assessed % of Avoided Admissions within 24 hours % of avoided admissions within 72 hours PPH front of house TOCALS Number Assessed % of Avoided Admissions within 24 hours % of Avoided Admissions within 72 hours | 624 44% 10% 433 51.5% 56% | 754792.67 | -50060.67 | Sustaining a substantive TOCALS teams on both acute hospital sites has been a challenge. Not only from a cover perspective but also in terms of staff de-skilling from not having the direct community experience. We have established a Task & Finish group to look at providing the service in a different way. This will also look at rationalising the current resource to make it more cost effective and sustainable over time. This includes looking at a duty rota model of cover from community into the ‘front door’ of the hospital and also looking at skill mix of current staff to ensure most effective and efficient use of resources.
|  | Careline | carmarthenshire | Manage a team that will provide Advice to at least 10,000 clients annually | The service is now fully operational on a 24/7 basis. This enables the service to support partner agencies such as 111 and WAST in an integrated way to timely access to IAA. Over the full year the service has undertaken 10,537 proportional assessments and provide just advice to many more customers. | 67585.59 | -67585.59
| 108761 | Acute Response Team Enhancement | Carmarthenshire | Number of Patients treated at home with IV antibiotics Number of avoided admissions Number of facilitated discharges | 319patients 149 patients 170 patients | 118760.92 | -9999.92 | The 3.4 WTE extra posts (1.0 WTE band 6, 2.4 WTE band 5) have ensured that an extra registered nurse is on duty in between the hours of 07.00 and 22.00, 7 days a week. The average length of stay per patient on the ART IV caseload is 7-10 days. During Q4 the total bed days saved for patients receiving IV antibiotics is 833 to 119 bed days saved in both Acute Hospitals. This includes both facilitated discharges and admissions avoided
| 24000 | Information & Advice Officer (Carers) | Carmarthenshire | Number of individuals referred Improved response from carers seeking assessment | 7 | 22880 | 1120 | The role is emerging as one of facilitation – ensuring better outcomes for carers through the promotion of and support for best practice. Linking with the operational teams the worker has developed relations with Carers Champions and is implementing a schedule of networking meetings to reinforce the presence of the role as a support mechanism. Carers are reporting better outcomes (see example case) whilst practitioners are valuing additional resource to assist them in supporting carers and understanding how creative solutions can be applied in supporting unpaid carers.
|  | Clinical Psychology Service for Chronic Conditions | Carmarthenshire | Establishment of referral pathways from Intermediate Care to Psychological Services Training delivered to Intermediate Care teams to allow early identification of psychological risks and ability to deliver early interventions Access to psychological support relating to a long term condition Improved anxiety, depression and wellbeing | 61 Diabetes 36% Cardiac 19% Respiratory 15% Primary Care 16% Social Care 7% Other 7% Percentage referrals due to depression and/or anxiety = 69% Percentage of referrals due to poor self-management & requiring psychological intervention for behaviour change = 31% Training scheduled for 10 specialist Diabetes nurses service (April) and for 20 social care CRT staff (June) | 32602.28 | -32602.28 | Data for whole service indicates over 60% of people with depression improves. As depression increases costs per person, per annum by £1.5K in chronic conditions, service contributes to reduced service costs. Economic research in impact of depression in chronic conditions conducted by King’s Fund.
| 37085 | Demand Capacity | Carmarthenshire | To be confirmed |  | 22954.76 | 14130.24 | The resource provided by this investment has been invaluable in providing intelligence on the ‘current state’ with regards to whole system Health & Social Care demand. This will be further built on now that Hywel Dda UHB & Carmarthenshire specifically, is piloting the Integrated Pathway for Older People (IPOP) on behalf of the National Unscheduled Care Board. The IPOP will provide a planning and performance framework across the whole system of unscheduled care and will also enable us to measure the impact of ICF investment. The IPOP Partnership Pilot group has its inaugural meeting on the 2nd May and this includes representatives from across Clinical Disciplines including general medicine and gerontology , Senior Management across H&SC Primary Care and Performance Analyst colleagues.
| 0 | Assessment Beds (Slippage) | Carmarthenshire |  |  | 53419 | -53419
| 294000 | Third Sector Core Community Resource Team | Ceredigion | Number of individuals supported | 246 | 294000 | 0
|  |  |  | Number of interventions | 2004
|  |  |  | Number of hours to support clients | 8268
|  |  |  | Number of external referrals | 49
|  |  |  | Number of external signposts | 46
|  |  |  | Number of LD individuals supported | 0%
|  |  |  | Number of carers identified* | 49
|  |  |  | Percentage of people who felt involved in decisions about their care and support* | 87% |  |  | *Measures were introduced in second quarter, figures related to Qtr 2 – Qtr 4 inclusively
|  |  |  | Percentage of people reporting that they are able to do things that matter to them* | 87%
| 58366 | Third Sector Integration Facilitators | Ceredigion | Number of professional contacts made | 2991 | 59040.23 | -674.23
|  |  |  | Number of clients / patients supported at Porth Gofal where a 3rd sector service is suggested and taken up | 59
| 116080 | Vascular Podiatry | Whole Region | This is a new service and one that is unique across Wales, therefore provisional outcomes and preparation for a new service is underway. Outcomes that will be reported in the future will be: Reduced length of stay of vascular patients on acute wards as a result of new patient care pathway Reduction in the number of referrals to Vascular Service as a result of increased vascular podiatrist in community clinics Reduction of District Nursing visits relating to chronic leg ulceration Reduction/ stabilisation in number of amputations within the region | No information received | 120122.89 | -4042.89
| 122290 | Community Falls Clinics (“Safe and Steady Clinic”) | Ceredigion | Number of clinics | 68 | 100618.98 | 21671.02
|  |  |  | Number of referrals received | 224
|  |  |  | Number of people seen in clinic | 213
|  |  |  | Number of fallers | 112
|  |  |  | Number of falls (in previous 12 months) | 421
|  |  |  | Percentage of clinic attenders screened with a Fear of falling (quantified via the FES International tool) | 53.7
|  |  |  | Percentage of clinic attenders with an Instrumental Activities of Daily Living Scale / Barthel Index / 3m TUG / Berg / 10m TWT scores | 92.2
|  |  |  | Number of people seen in follow up clinic | 5
| 327728 | Accessing Alternatives to Admission | Ceredigion | Number of new patients discussed (front of house) - Ceredigion | 146 | 280100.22 | 47627.78 | The AA2A service did not function fully during quarter 4 due to recruitment issues. The service will be re-developed in 2018-19.
|  |  |  | Number of new patients discussed (front of house) - Powys | 68
|  |  |  | Number of new patients discussed (front of house) - Gwynedd | 32
|  |  |  | Number of new patients admitted, but identified by AA2A as complex and assigned Community Specialist Nurse as lead | 110
|  |  |  | Number of new patients admitted, but identified by AA2A as complex and assigned OT as lead | 45
|  |  |  | Number of new patients admitted, but identified by AA2A as complex and assigned Physio as lead | 88
|  |  |  | Number of new patients admitted, but identified by AA2A as complex and assigned Social Care as lead | 73
|  |  |  | Total Number of new patients admitted, but identified by AA2A as complex and discharge managed by AA2A | 261
|  |  |  | Number of new patients admitted, but identified by AA2A as complex and discharge managed by AA2A - Ceredigion | 154
|  |  |  | Number of new patients admitted, but identified by AA2A as complex and discharge managed by AA2A - Powys | 61
|  |  |  | Number of new patients admitted, but identified by AA2A as complex and discharge managed by AA2A - Gwynedd | 46
|  |  |  | Number of patients discharged (front of house) | 152
| 231617 | Interim Placement Scheme | Ceredigion | Number of patients who used the nursing bed scheme* | 63 | 227977.57 | 3639.43 | * These figures are for the entire scheme and not exclusive of those ‘spot purchased’ and funded specifically from ICF
|  |  |  | Number of patients who used the residential bed scheme | 15
|  |  |  | Number of patients discharged from the nursing bed scheme* | 60
|  |  |  | Number of patients discharged from the residential bed scheme | 15
|  |  |  | Average LOS on the nursing bed scheme* | 32.75
|  |  |  | Average LOS on the residential bed scheme | 36.3
|  |  |  | Percentage of patients in the nursing bed scheme with a care plan* | 100
|  |  |  | Percentage of patients in the residential bed scheme with a care plan | 100
|  |  |  | Percentage of people on the nursing bed scheme who returned to their home on discharge* | 30
|  |  |  | Percentage of people on the residential bed scheme who returned to their home on discharge | 68.3
|  |  |  | Percentage of people on the nursing bed scheme who went into residential care on discharge* | 3.5
|  |  |  | Percentage of people on the residential bed scheme who went into residential care on discharge | 6
|  |  |  | Percentage of people on the nursing bed scheme who went into nursing care on discharge* | 56
|  |  |  | Percentage of people on the residential bed scheme who went into nursing care on discharge | 7
|  |  |  | Percentage of people on the nursing bed scheme who were discharged to a DGH* | 2
|  |  |  | Percentage of people on the residential bed scheme who were discharged to a DGH | 7
Slippage |  | Carers Resilience & Wellbeing Project Phase 2 Feasibility Design Study | Ceredigion | No. sessions / workshops held (target 6) | 6 | 10900 | -10900
|  |  |  | No. partners / young carers / carers engaged / consulted / participated in workshops (target 50) | 71
Slippage |  | Ceredigion Caring Communities Innovation Fund 17-18 (funded by slippage from AA2A) | Ceredigion | No. initiatives supported (target 4) | 5 | 43000 | -43000
|  |  |  | No. individuals supported | 119
No. initiatives mainstreamed
Slippage |  | VIPAR Increasing provision of pulmonary rehabilitation in rural areas using video conference | Ceredigion | Delivery of 1 programme in community hall | 1 | 9320 | -9320
|  |  |  | Enrol 8 COPD patients to the spoke site | 7
|  |  |  | Percentage of patients completing 10 our of 13 sessions (target >75%) | 86%
Slippage |  | Effective Referral Conversations (training for staff undertaking MDT decision making) | Ceredigion | 2 day training session to be held in Ceredigion | Completed | 3991 | -3991
|  |  |  | Enrol 20 + staff members onto the course | 25
Slippage |  | Telehealth Led Palliative Services | Ceredigion | Development of an awareness campaign (with Aberystwyth University) | Completed | 5053 | -5053
TOTALS | 5760496.4 |  |  |  |  | 5880168.6606 | -117877.6606
Note on D5: KennedyPR: Where possible, please group activity under a common theme, such as -prevention -falls -reducing isolation
Note on E5: KennedyPR: If activity is across some LAs but not all in the region, please record as "regional" activity
Note on F5: KennedyPR: Please use a new line for each identified outcome or output. Limit outcomes to 3 per project. Further detail can be included in column N if necessary
Note on J5: KennedyPR: Please record any slippage, virement or ngoing issues impacting on delivery, and any other information

## LDIS, Complex and Carers
Regional Allocation | Total regional spend |  | Regional under/overspend | ICF 2017-18 monitoring |  |  |  | 2018-06-01 |  | learning Disabilties
2162907.64 | 641148.85 |  | 1521758.79 | West Wales - Learning Disabilities, Children with Complex Needs, and Carers | [5 empty] | Children with complex needs
Region |  |  |  |  | Performance |  |  |  |  | carers
West Wales |  |  |  |  | Projected outcomes and outputs |  | Expenditure
Ref | Funding Allocation | Area | Service / activity description | Specific area or whole region? | Include a benchmark or target for reference against | Outcomes to date Q4 | Spend to Date Q4 | Over or underspend | Further information
| 40000 |  | Supported Employment Social Enterprise (Café/LD Partnership Board support) | Pembrokeshire | Supported employment for 10 individuals. | Supported 6 people with work experience on the LD website and 6 people on the Meads Café project. Supported 10 people with paid work opportunities across LD website development and development of mead café Due to the delay in opening the café the benefit to older People/LD for social interaction will be seen in 2018/19. Website shown to 6 groups including the easy read group. Website is being viewed by | 19976.4 | Expected to by £19K underspend | Underspend due to the delay in capital expenditure due to late approval
Support volunteering for 10 individuals.
| 150000 |  | Behavioural Intervention Service | Whole Region | Education & training regarding Positive Behaviour Support for children, families and professionals across all sectors. Improved physical, mental and emotional well-being for children and their families | All staff are in post with 63 referrals recieved to date and 35 families recieving direct support . Staff are currently undertaking BTEC level 5 in Positive Behaviour Support. | 150000.24 | -0.24 | Sensory equipment has been purchased to establish a loan library and Positive Behaviour Support Workshops are being run across all 3 counties for parents, carers and staff. Consultation and training is being delivered to other professionals in Education, Social Care, Health and the third sector to ‘prevent’ the need for referrals to our service.
| 35000 |  | Admiral Nurses | Whole Region |  | Funding re-allocated to Fullfilled lives Dementia project supporting those living with the condition in Carmarthenshire. Funding in Ceredigion enabled the delivery of social activities delivered by social enterprise Ray Ceredigion. | 34733 | 0 | Due to the prolonged recruitment processes within HDUHB, staff would not be appointed until February 2017, giving no time to deliver the project. Underspend was reallocated to alternative support for families dealing with dementia.
P6 | 87918 |  | Accommodation and Efficiency | Pembrokeshire | Citizens live in a home that best supports them to achieve well-being Citizens get the right care and support, as early as possible | The Project worked with 28 individuals over the course of the year, reviewing packages to ensure that (a) care quality was of a high standard, and (b) care packages met service user need and were supporting progression. Financial impact of project work in 17/18 was £88,863. Evaluation methods are in development. | 86344.43 | 1573.57 | Full project restructure and rebranding from Accommodation and Efficiency Project to Progression Project. Internal team of Senior Social Work Practitioner, Assessor Care Coordinator and part-time Commissioning Officer recruited and in post. Significant headway made in establishing processes and procedures. Delays in recruitment and staff changes within project team have impacted on measureable outcomes.
P11 | 20000 |  | Complex Needs Accommodation Project | Pembrokeshire | Citizens live in a home that best supports them to achieve well-being Citizens get the right care and support, as early as possible Development of Accommodation Strategy | Accommodation voids management process developed in Learning Disabilities to ensure that service users are matched to homes that support them Accommodation Needs Supply & Demand Analysis currently in draft. This will support development of local and regional Accommodation Strategy Links made with regional accommodation strategy work | 10938.24 | 9061.76 | Part time (2 days/ week) Accommodation Officer in post Nov 2017 Data gathering and analysis (‘mapping and gapping’) of supply and demand of accommodation in Pembrokeshire to support development of Accommodation Strategy. Two whole-service Learning Disabilities needs mapping workshops took place Supporting development of process with providers by examining mismatch between income and expenditure in Learning Disabilities Accommodation, ensuring that service users are accessing all benefits to which they are entitled & being supported to pay top ups.
| 13000 |  | Assistive Technology | Pembrokeshire |  | No figures received | 10489.16 | 2510.84
| 76308 |  | Positive Behaviour Service | Carmarthenshire | Reduction in behaviour that challenges. Reduction in the number of people living away from their County of origin; A reduction in placement breakdowns and / or admissions to hospital & Reduction in cost of packages for people who may challenge. | Team manager in place since December 17. One full-time PBS support worker in post and another in the recruitment process. One vacancy – looking to recruit shortly. Currently actively working with 3 individuals who challenge services. Looking at potential daytime opportunities for one young man who leaves school this summer. Outcomes are likely to be enhanced staff skills/abilities to work with people who challenge and prevent placement breakdown and reliance on out of county commissioning | 12891.98 | 63416.02 | This team is already actively working with 3 people but is also looking at other people being identified. They are supporting staff to engage more effectively and this is already having a positive effect on the time spent disengaged. They are working closely with Parents, PBIS and Care Manager on identifying possible daytime opportunities following the young person leaving school. Other people are being put forward for further intervention. Additional staff training and support is showing increased confidence in staff team.
| 19996 |  | Occupational Therapist for Sensory Impairment | Carmarthenshire | Measures: Number of staff trained & Number of Sensory assessments, number of sensory plans, reduced frequency and intensity of incidents of challenging behaviour. Outcomes: staff feeling confident using sensory interventions, individual service users having the ability to make choices / having more control over their environment and lives, individuals having more opportunities within their community. | We have been unable to recruit an OT, however, additional equipment has been purchased using slippage monies. Outcomes are that individuals with Sensory processing difficulties have facilities which enable a wide variety of opportunities to enhance self-expression, make choices and experiences which are difficult to access in their everyday lives. | 0 | 19996 | Additional overhead interactive projectors have been purchased. These offer a variety of interactive activities providing sensory stimulation for people who have profound and multiple needs.
| 318200 |  | Integrated Autism Service (IAS) | Whole Region |  | Reported to WLGA | 315775.4
| 760422 |  |  |  |  | TOTALS | 641148.85 | 96557.95
Note on D5: KennedyPR: Where possible, please group activity under a common theme, such as -prevention -falls -reducing isolation
Note on E5: KennedyPR: If activity is across some LAs but not all in the region, please record as "regional" activity
Note on F5: KennedyPR: Please use a new line for each identified outcome or output. Limit outcomes to 3 per project. Further detail can be included in column N if necessary
Note on J5: KennedyPR: Please record any slippage, virement or ngoing issues impacting on delivery, and any other information

## Capital
Regional Allocation | Total regional spend | Regional under/overspend | ICF 2017-18 monitoring | [5 empty] | 2018-06-01
1301000 | 0 | 1301000 | West Wales - Capital projects
Region |  | Category |  | Performance
West Wales |  | Capital |  | Projected outcomes and outputs | Outcomes to date |  |  | Expenditure
Ref | Funding Allocation | Service / activity description | Specific area or whole region? | Include a benchmark or target for reference against | Q4 | Spend to date | Further information / progress narrative | Spend to date | Over or underspend
| 30000 | PIVOT - Pembrokeshire Intermediate Voluntary Organisations Team | Pembrokeshire | No. of adaptations provided | 48 | 30000 |  |  | 0
| 10000 | Caring Communities Innovations Grants | Pembrokeshire | No. of grants distributed Value of grants | 3 | 15750 |  |  | -5750
(includes management fee for grant fund administration)
| 35000 | Supported Employment Social Enterprise (Café/LD Partnership Board support) | Pembrokeshire | Create a café space that can be used by older people and people with LD to reduce isolation and provide supported employment | Supported 6 people with work experience Supported 6 people with paid work opportunities in development of mead café Due to the delay in opening the café the benefit to older People/LD for social interaction will be seen in 2018/19. | 34995.65 | Formal café opening set for May. Delay due to delay in capital being approved and additional work requirements. |  | 4.35
| 20000 | Behavioural Intervention Service | Whole Region | Increased service provision for children with complex sensory needs (and so may have behaviour that challenges) Person Centred Care Increased well being for child and their family. | Recruited qualified occupational therapist, under took research in to the most appropriate equipment whilst working in partnership with families, Social Care, Education and Health colleagues. | 13458.46 |  |  | 6541.54
| 224000 | Accommodation Options Project | Pembrokeshire | 1. Purchase property 2. Install adapted pods. | 1. Property purchased, majority of renovation work undertaken, adaptations being installed. 2. Due to issues over higher than originally indicated costs from supplier, the scheme as it stood did not represent value for money, so was halted. | 216116.59 | Intention is to resubmit capital bid for 18/19 and undertake competitive tendering exercise. |  | 7883.41
| 20000 | Assistive Technology & Just Checking Service | Carmarthenshire | To trial new technologies in the County by identifying the “gaps” in the provision of equipment, that could be met with new types of Telecare equipment. This equipment will be purchased and tested with clients, which will allow the service to develop new ranges of equipment types that can be used by prescribers in the future. Specific areas such as dementia care has been identified so that the equipment used can be measured against the specific outcomes for the client / service. | New types of assistive technology equipment purchased. New items such as clocks and tracking devices for those with dementia were purchased and trialled as part of a large project, which was successfully. Just checking systems and similar makes were purchased to give various social care and health teams to give information on the movements of a client. | 47458.04 |  |  | -27458.04
| 14000 | New software for equipment service | Carmarthenshire | Purchase & Implement new Software system Prevention of hospital admission through timely ordering and delivery of equipment to individuals at home | IT system purchased. Nursing and Hospital staff will receive training so that they can access the IT system remotely and order on line. This will stop the need for faxes which currently go to one central office before coming to us. The new It system will be a much more efficient way of sending and receiving orders as they will be instant and will help the prescriber understand what equipment is suitable for their client. | 15000 |  |  | -1000
| 60000 | Assistive Technology | Pembrokeshire |  | No figures received. | 66893.36 |  |  | -6893.36
| 100000 | Independent Living – Step Down facilities for LD (Carmarthenshire) | Carmarthenshire | Enable greater choice of accommodation to individuals with LD & Complex Needs Enable individuals to remain in their Community Enable greater independence of individuals |  | 6347.07 | This project has not progressed and therefore the underspend has been re-allocated to new schemes. |  | 93652.93
| 180923 | Intermediate care Community Beds (Step up/Step down) (Carmarthenshire) | Carmarthenshire | Individuals are discharged to an appropriate place to regain independence |  | 0 | This project has not progressed and therefore the underspend has been re-allocated to new schemes. |  | 180923
| 34000 | Assessment & Respite Service | Carmarthenshire | To provide existing services to users and carers in a trusted setting | Adaptations have been made to the structure of the bedrooms and lounges at Tir Einon to allow for supporting people with various needs at the same time. Outcome is that the facility is able to provide a greater range of services and thus support individuals and families in need of respite at the same time. | 27161.92 | Some bedroom windows have been changed to allow for ‘integral blinds’ supporting individuals dignity and a more enclosed garden with a covered area. An additional door has been fitted to an internal corridor to allow for people to have individual lounges when they are using the facility at the same time. Additional robust fixtures and fittings have been purchased for bedrooms to allow for items, such as the tv, to be placed securely. | 0 | 6838.08
| 280000 | Community Equipment - general provision & releasing time to care | Carmarthenshire | New community equipment purchased to meet the needs of patients being discharged from hospital, for clients in their own home that need equipment in order that they can stay at home safely and reduce the need to enter into a care setting. | All equipment types identified and purchased. Pressure care equipment and profiling beds were purchased and as a direct result more clients were looked after at home, stopping the client entering into a hospital setting, and allowing patients to return home at an earlier opportunity. The purchase of new manual handling equipment (releasing time to care) allowed more clients to be looked after by family members, reducing the need for care packages and helping patients to return home from hospital at the earliest opportunity. | 347889.46 |  |  | -67889.46
| 134612 | Maintaining independence through provision of accommodation based solutions | Ceredigion | 120 Home Safety assessments carried out. | 25 | 134612 |  |  | 0
|  |  |  | 100 Handyperson interventions completed | 24
|  |  |  | 30 Emergency Repair Assistance grants delivered | 6
|  |  |  | Satisfaction questionnaire (customer satisfaction with handy person / home safety scheme | 91%
| 108182 | Maintaining independence through provision of equipment to support people in their own homes | Ceredigion | Purchase beds which can be safely used with a hoist | 10 | 108182 |  |  | 0
|  |  |  | Purchase of other equipment to support complex patient needs | 55
| 40000 | Releasing Time to care | Pembrokeshire |  |  | 39994.4 |  |  | 5.6
| 9460 | Telehealth Equipment | Ceredigion |  |  | 10899.33 | Slippage |  | -1439.33
|  | Llanelli Cycle project | Carmarthenshire | Improved health and social benefits from disability cycle use. Choice of activity integration. Measurement of use of cycles. | The delivery of the project to clients is due to commence in May 2018. | 59953.7 | Delivery of disability cycles 26th March 2018. Disability cycles are now on site at Pembrey Country park and will be hired from the Ski Centre. Meetings arranged for April, hire to commence in May 2018. Health benefits will be measured on a number of case studies where heart rate and weight can be monitored at the commencement of the project and then as an ongoing monitor over 3, 6, 9 and 12 months. |  | -59953.7
|  | Sensory Integration pathway | Carmarthenshire | Outcome is that a greater number of individuals will be able to access sensory activities thus enhancing individual well-being, experiences and choice making opportunities. | Additional equipment purchased to support sensory opportunities. | 17810.86 | This equipment is now available in services in Llanelli, Ammanford and Carmarthen. |  | -17810.86
|  | Care and repair Temporary ramps | Carmarthenshire | Ability to respond quickly and economically with regard to requests for ramped access to domestic properties. Temporary nature of ramps allows re-cyclability. Design of system means that there are none of the disadvantages of a ‘wet’ ramp construction. Allows the potential for quicker hospital discharge, prevention of accident (client and carers) and ability to stay in the accommodation of choice. | Ramping kits purchased and some in use (ref to Case Study). | 10000 |  |  | -10000
|  | Garreglwyd | Carmarthenshire |  | Soundproofing 2 x rooms on first floor (Walls & Floor). New Corridor door. Turning 3 rooms into 2 bathrooms. Hacking off and Re-Rendering front aspect of the building. New staff sleeping in room with en-suite facilities New Kitchen for CYP. New DDA compliant toilet. New Flooring in activity room. | 91061.7 | At present, work is continuing and nearing completion. Kitchen installation is happening this week and also some snagging work. The Re-Rendering is complete, but it is still in need of painting. |  | -91061.7
|  | Leg Ulcer Chair | Carmarthenshire | Enable greater choice of care environments to individuals with Complex Leg Ulcer Needs Enable individuals to remain in their Community Enable greater independence of individuals |  | 6240.25 | Leg Ulcer chair arrived at the very end of March and therefore has only just gone into service, but will prove an enormous improvement to both the quality of treatment provided and the ability of the Nursing team to provide the care required. |  | -6240.25
| 1300177 |  |  |  |  | 1299824.79 |  | 0 | 352.21
Note on C5: KennedyPR: Where possible, please group activity under a common theme, such as -prevention -falls -reducing isolation
Note on D5: KennedyPR: If activity is across some LAs but not all in the region, please record as "regional" activity
Note on E5: KennedyPR: Please use a new line for each identified outcome or output. Limit outcomes to 3 per project. Further detail can be included in column N if necessary
Note on H5: KennedyPR: Please record any slippage, virement or ngoing issues impacting on delivery, and any other information

## Notes and references
Please submit to | icf@wales.gsi.gov.uk
ICF guidance |  | http://gov.wales/topics/health/socialcare/working/icf/?lang=en
as per para 2.2 of guidance, outcomes should be from the outcomes framework |  | http://gov.wales/topics/health/socialcare/well-being/?lang=en